## Daily log
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Date | Weather | Temp | Trade | Crew size | Hours | Work performed | Location | Equipment | Deliveries | Inspections | Delays | Safety | Superintendent
Total

## Schedule
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
ID | Task | Predecessor | Start | Finish | Duration (days) | Responsible | % complete | Status
1 | Mobilisation
2 | Site work and utilities
3 | Foundations
4 | Structure
5 | Envelope
6 | Rough-in (MEP)
7 | Interior finishes
8 | Commissioning
9 | Punch list and closeout
Formulas:
Duration (days) = IF(AND([Start]<>"",[Finish]<>""),NETWORKDAYS([Start],[Finish]),"")
Status = IF([Task]="","",IF(H5>=1,"Complete",IF(AND([Finish]<>"",TODAY()>[Finish]),"Late",IF(H5>0,"In progress","Not started"))))

## Budget
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Cost code | Description | Original budget | Approved changes | Revised budget | Committed | Cost to date | Forecast at completion | Variance
01 | General conditions
02 | Site work
03 | Concrete
05 | Metals
06 | Wood and plastics
07 | Thermal and moisture
08 | Openings
09 | Finishes
22 | Plumbing
23 | HVAC
26 | Electrical
Total

## Change orders
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
CO no. | Description | Reason | Submitted | Amount | Schedule days | Status | Approved | Revised contract sum
Total

## RFI log
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
RFI no. | Subject | Reference | Submitted | To | Response due | Responded | Days open | Impact

## Submittals
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Submittal no. | Spec section | Item | Subcontractor | Submitted | Reviewer | Returned | Action | Resubmit due | Days in review

## Punch list
Construction Project Management Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Item | Location | Deficiency | Trade | Due | Completed | Verified by | Status