## Board
Kanban Board Templates
Column values: Backlog, Ready, In progress, Review, Done. The WIP sheet counts them against limits.
Card | Owner | Size | Column | Class of service | Created | Started | Finished | Cycle time (days) | Blocked (Y/N) | Notes

## WIP
Kanban Board Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Column | Limit | Cards now | Over limit?
Ready | 5
In progress | 3
Review | 2

## Cycle time
Kanban Board Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Measure | Days
Average cycle time (done cards)
85th percentile
Throughput (cards done)
Blocked cards now

## Classes of service
Kanban Board Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Class | Rule | Target cycle time (days)
Expedite | One at a time; jumps the queue | 1
Fixed date | Start by the latest date that makes the deadline
Standard | First in, first out within WIP limit | 10
Intangible | Improvement; pulled when nothing else is ready