## Project kickoff checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Sponsor and project manager named
Purpose and objectives agreed and written
Scope and exclusions signed off
Budget approved and source of funds confirmed
Team assigned with availability confirmed
Stakeholders identified and communication plan agreed
Risks reviewed and top risks have owners
Tools, repositories and access set up
Kickoff meeting held and minutes circulated

## Project planning checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Work breakdown structure complete to deliverable level
Estimates reviewed by the people doing the work
Schedule built with dependencies and critical path identified
Resource plan matches the schedule
Budget baseline set with contingency
Quality criteria defined for each deliverable
Change control process agreed
Baseline approved by sponsor

## Weekly project checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Schedule updated with actual progress
Budget forecast updated
Risks and issues reviewed; new ones logged
Decisions needed listed with owners
Status report sent
Next week's priorities agreed with the team
Stakeholder questions answered

## Deliverable review checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Deliverable matches the agreed definition
Acceptance criteria tested and evidence attached
Reviewed by the named approver
Defects logged and resolved or accepted
Documentation complete
Handover to the owner recorded
Sign-off obtained

## Risk review checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Each risk has a description, likelihood, impact and owner
Mitigations are actions with dates, not intentions
Risks that have occurred are moved to issues
New risks from the last period added
Top five reviewed with the sponsor
Contingency drawdown recorded

## Project closeout checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
All deliverables accepted in writing
Final invoices issued and paid or scheduled
Contracts and purchase orders closed
Documentation archived
Lessons learned session held and written up
Team released and recognised
Benefits tracking handed to the owner
Sponsor sign-off on closure

## Go-live checklist
Project Checklist Templates
Status counts: Done =COUNTIF(D:D,"Done"), Open =COUNTIF(D:D,"Open")
Item | Owner | Due | Status (Done / Open / N/A) | Evidence or note
Acceptance testing complete and signed
Rollback plan written and tested
Support team briefed and on call
Users trained and communications sent
Data migrated and verified
Monitoring in place
Go or no-go decision recorded with attendees
Post-go-live review scheduled