## Three-point
Project Estimate Templates
Project standard deviation is the square root of the summed variances. Expected plus one standard deviation covers about 84% of outcomes; plus two covers about 98%.
WBS | Work package | Optimistic (hours) | Most likely | Pessimistic | Expected | Std dev | Variance | Role | Assumptions
Total

## Confidence
Project Estimate Templates
References assume the total row of Three-point sits at row 31 (25 blank rows). Adjust if you add rows.
Measure | Hours
Expected total
Project standard deviation
Estimate at 84% confidence
Estimate at 98% confidence

## Cost
Project Estimate Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Role | Hours | Rate | Cost
Total

## Expenses
Project Estimate Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Expense | Basis | Amount
Software and licences
Hardware
Travel
Subcontractors
Other
Total

## Summary
Project Estimate Templates
Totals reference Cost!D16 and Expenses!C13; adjust if you add rows to those sheets.
Line | Amount
Labour
Expenses
Subtotal
Contingency % | 0.15
Contingency
Margin % | 0.2
Margin
Total

## Assumptions
Project Estimate Templates
Template from WorkIntel Hub (workintelhub.com). Free to use and adapt. Not legal advice.
Assumption | Impact if wrong | Owner | Confirmed (Y/N)